## Error Log Final
No | Date | Modality | HHID | uuid | Enumerator | Logged by: | Comments | Action Required | Other comments | Action Taken | Closed?
1 | 2023-07-24 | F2F | General |  |  | Nicole | There are 19 out of sample submissions with similar HHID manually added, why this happened initially? | Maria to check and clarify
2 | 2023-07-24 | F2F | ECU0112347 | 7b401430-5f52-4a96-a8af-538614e59c44 | JOSSELYN TENELEMA | Nicole | RESPStatus missing, but completed the survey, how possible? | Maria to check and clarify
3 | 2023-07-24 | F2F | ECU0190821 | a073c4cf-7b38-42d4-8c48-b64ea15357d1 | VERÓNICA GUERRERO | Nicole | HHInc_PCT missing but all others completed, how possible? | Maria to check and clarify
4 | 2023-07-07 | Remote |  | f762f176-7368-4ade-930c-3d246f4a9d4d | DAYANARA BRIONES | Nicole | Completed but no HHID - How is this even possible? | Look into the specific response and check with the enumerator
5 | 2023-07-07 | Remote |  | 1de2d9cd-18ba-4721-a45e-d4d6c814cb3c | ANTONY VEGA | Nicole | Not completed - but no HHID, we should avoid this! | Look into the specific response and check with the enumerator
6 | 2023-07-24
7 | 2023-07-24
8 | 2023-07-24
9 | 2023-07-24
10 | 2023-07-24
11 | 2023-07-24
12 | 2023-07-24
13 | 2023-07-24
14 | 2023-07-24
15 | 2023-07-24
16 | 2023-07-24
17 | 2023-07-24
18 | 2023-07-24
19 | 2023-07-24
20 | 2023-07-24
21 | 2023-07-24
22 | 2023-07-24
23 | 2023-07-24
24 | 2023-07-24
25 | 2023-07-24
26 | 2023-07-24
27 | 2023-07-24
28 | 2023-07-24
29 | 2023-07-24
30 | 2023-07-24
31 | 2023-07-24
32 | 2023-07-24
33 | 2023-07-24
34 | 2023-07-24
35 | 2023-07-24
36 | 2023-07-24
37 | 2023-07-24
38 | 2023-07-24
39 | 2023-07-24

## Duplicates
No | Date | Modality | HHID | uuid | Enumerator | Logged by: | Responses | Other comments | Action Taken | Closed?
1 | 2023-07-24 | F2F | ECU010224 | f158bc74-4d08-479b-96dd-23787d3880af | VÍCTOR FLORES | Nicole
| 2023-07-24 |  | ECU010224 | d2012955-cf1e-48ee-bdda-4d8dce28d5ee | JOSSELYN TENELEMA | Nicole
2 | 2023-07-24 | F2F | ECU0190705 | 57d49e89-cc4e-4aa2-b01b-fef4e1ed2fe6 | JOSUE VARGAS | Nicole
| 2023-07-24 |  | ECU0190705 | 0f5aaa1c-1fd1-4981-a1db-ad6b7f96f10b | ISABEL BURBANO | Nicole
3 | 2023-07-24 | F2F | ECU0190737 | 0fcddc81-d993-4c10-bcf5-57347384faaf | JOSUE VARGAS | Nicole
| 2023-07-24 |  | ECU0190737 | 87bd5280-8278-4afe-b40e-f5988a7905b3 | VERÓNICA GUERRERO | Nicole
4 | 2023-07-24 | F2F | ECU0190764 | ddec9d93-5ff8-469b-a89c-5ff69c05e8a0 | KATHERINE CHALA | Nicole
| 2023-07-24 |  | ECU0190764 | f87c3879-daff-497d-86b9-9e30f5b9d0cc | KATHERINE CHALA | Nicole
5 | 2023-07-24 | F2F | ECU0190765 | 6a0c3dd0-a803-46e2-8fea-ca33b8839df8 | KATHERINE CHALA | Nicole
| 2023-07-24 |  | ECU0190765 | ce01ec22-a8c7-4239-9b78-f65b64962be9 | ISABEL BURBANO | Nicole
6 | 2023-07-24 | F2F | ECU020144 | d1e66b37-4d8a-40ca-9d4a-25a469494647 | JEFFERSON TENORIO | Nicole
| 2023-07-24 |  | ECU020144 | 94b12b58-099c-490a-a338-38fe94c0872a | ERICK GUERRA | Nicole
| 2023-07-24 |  | ECU020144 | 614448c3-4f46-4a7a-b9e7-0843e1031cc4 | JEFFERSON TENORIO | Nicole
7 | 2023-07-24 | F2F | ECU020160 | 34bba9cb-6703-4423-9ddd-4fb859fe82d1 | ERICK GUERRA | Nicole
| 2023-07-24 |  | ECU020160 | 00f31eb6-282f-4aaa-88e9-2ca5bf8fcfb3 | JEFFERSON TENORIO | Nicole
| 2023-07-24 |  | ECU020160 | 2376096a-ae83-4465-b38c-62aa25017bd5 | ERICK GUERRA | Nicole
8 | 2023-07-24 | F2F | ECU0212373 | 5199b75b-7cd6-4986-921d-15cb5909c0e3 | JEFFERSON TENORIO | Nicole
| 2023-07-24 |  | ECU0212373 | d0396879-09f0-4bf9-acf1-10ef68d88556 | JEFFERSON TENORIO | Nicole
| 2023-07-24 |  | ECU0212373 | d7b33ab9-df1a-43f2-8717-8ad502ff11ce | ERICK GUERRA | Nicole
9 | 2023-07-24 | F2F | ECU0312397 | 8635e577-28dc-445f-9379-c2df9c503119 | VERÓNICA GUERRERO | Nicole
| 2023-07-24 |  | ECU0312397 | cc38c82a-8439-472b-9145-4479a306f7c5 | VERÓNICA GUERRERO | Nicole
10 | 2023-07-24 | F2F | ECU2190800 | 4c117925-9b68-4277-b8c9-c1d5fb30ddf2 | ERICK GUERRA | Nicole
| 2023-07-24 |  | ECU2190800 | 5e9e28c9-651f-436f-a56a-ff85cf87e3f6 | OMAR ANDRADE | Nicole
11 | 2023-07-24 | F2F | ECU2190802 | 5d2faf52-1ba2-49a8-aed6-59d03b8af5e8 | JEFFERSON TENORIO | Nicole
| 2023-07-24 |  | ECU2190802 | 987f04c1-3b51-4a03-bd39-e132097deb8a | JEFFERSON TENORIO | Nicole
12 | 2023-07-24 | Remote | ECU00941 | 9a887a11-4a44-413b-ac49-31a59b4125a8 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU00941 | 5b8d7ef8-0717-446d-b931-3ea3f8d1174b | ANTONY VEGA | Nicole
13 | 2023-07-24 | Remote | ECU01016 | de5b4569-41c8-4cc1-99e7-79e39fc89c49 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU01016 | 49ebb7e9-0823-49cf-a7b5-3f3a8210d6b2 | KATHERINE BALAREZO | Nicole
14 | 2023-07-24 | Remote | ECU01019 | 584143cf-e450-4e50-a97f-e1fb6657d6f5 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU01019 | e654b741-1a6a-40b5-9cfe-e6f6dd877df3 | KATHERINE BALAREZO | Nicole
15 | 2023-07-24 | Remote | ECU0134 | 562086e3-aeaa-4d31-a87b-2853eab773b6 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0134 | cfd17901-9dae-4122-9cc7-b60adfd988c7 | MELISSA MERA | Nicole
16 | 2023-07-24 | Remote | ECU0137 | 74302195-85fe-43cd-a405-8a0252c108dd | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0137 | d98d7f90-05bb-4adc-8f35-3c27bdad7576 | ANTONY VEGA | Nicole
17 | 2023-07-24 | Remote | ECU0138 | 9985b26c-95d5-48b6-82a5-27d5dfc6be82 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0138 | 214d31bf-2a7c-4171-8f16-4406f3c91fcc | ANTONY VEGA | Nicole
18 | 2023-07-24 | Remote | ECU0139 | e4b264c6-77c8-4979-9559-ad0bb344c22e | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0139 | e1a7c8e8-6073-408c-83e0-9eb6e48d03da | ANTONY VEGA | Nicole
19 | 2023-07-24 | Remote | ECU0140 | 53d9956e-7c15-4376-801a-23992cd2399d | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0140 | 2ac0cd14-b1f5-482e-9c91-cdcea3c90055 | ANTONY VEGA | Nicole
20 | 2023-07-24 | Remote | ECU0141 | 1f08711e-4361-45f4-bd21-616e557a7097 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0141 | bf416757-e1eb-4458-9b66-eac537491c3f | ANTONY VEGA | Nicole
21 | 2023-07-24 | Remote | ECU0142 | 98a337e7-8db7-41b2-98a7-99568feacbb4 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0142 | 3a22ac4a-1a27-46e7-b18a-3ba3e39fbfea | ANTONY VEGA | Nicole
22 | 2023-07-24 | Remote | ECU0143 | f9dcdbda-a8d7-4307-ba0c-20392053e52b | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0143 | bb1b6afc-96cc-413c-89c3-32c91c9f2be7 | ANTONY VEGA | Nicole
23 | 2023-07-24 | Remote | ECU0146 | 9cea020d-5fa4-4424-843f-70255688bce8 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0146 | 0866a623-2a1a-4a63-af29-e292ac47f858 | ANTONY VEGA | Nicole
24 | 2023-07-24 | Remote | ECU0147 | 449cd8e7-985f-4aea-9916-a1fafb316855 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0147 | 1ad689dd-4bbc-406e-83bc-4d1786ab6ef1 | ANTONY VEGA | Nicole
25 | 2023-07-24 | Remote | ECU01472 | 126188eb-13c6-40b1-833e-9838dbe07bde | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU01472 | 3275a41b-7240-4712-8d34-1611e2233794 | DAYANARA BRIONES | Nicole
26 | 2023-07-24 | Remote | ECU0148 | b6b9763c-d8c0-431e-b947-3bae62d583c8 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0148 | 7674a793-fd88-4c20-8a20-d6ae83b9ac0f | ANTONY VEGA | Nicole
27 | 2023-07-24 | Remote | ECU01492 | c4b616e2-6e8c-44dd-a478-f3b33dc64c29 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU01492 | fcf8430b-cc54-4a47-937b-9327e58af103 | STEPHANIE RAMOS | Nicole
28 | 2023-07-24 | Remote | ECU0169 | 230b2cd3-f44c-4201-b9f9-1730929b76e5 | MELISSA MERA | Nicole
| 2023-07-24 |  | ECU0169 | 34fd760b-2568-424c-be83-90632877cbb3 | DAYANARA BRIONES | Nicole
29 | 2023-07-24 | Remote | ECU0174 | 00bc2775-ad29-421b-88c0-cb76c882164a | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0174 | 77fd48a3-8442-493a-a5b4-a0a74537b082 | MELISSA MERA | Nicole
30 | 2023-07-24 | Remote | ECU0176 | ddeced62-f684-4421-9e57-79fb262bd76e | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0176 | 608ecac4-2924-4caf-8b92-e1774bb33fd3 | DAYANARA BRIONES | Nicole
31 | 2023-07-24 | Remote | ECU0179 | 56847497-fd1d-4e16-a862-b48497c02488 | MELISSA MERA | Nicole
| 2023-07-24 |  | ECU0179 | 404aaf88-fbc9-4957-8924-a5e598334220 | DAYANARA BRIONES | Nicole
32 | 2023-07-24 | Remote | ECU0180 | 9e90df8e-3b12-4d40-a805-b2250e884b40 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0180 | 139d1345-fe01-4b7f-b380-4501ec7d24a8 | MELISSA MERA | Nicole
| 2023-07-24 |  | ECU0180 | ae383d48-5269-4d5d-8612-86d8a642b13b | DAYANARA BRIONES | Nicole
33 | 2023-07-24 | Remote | ECU0185 | 61232642-5872-431d-88d3-8e1c738b071b | DANIEL TENELEMA | Nicole
| 2023-07-24 |  | ECU0185 | 0b781af0-43bd-4a1b-8b62-1fc37548176e | DAYANARA BRIONES | Nicole
34 | 2023-07-24 | Remote | ECU0187 | 63341311-3ace-49ec-a9ca-f1d065b89e70 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0187 | 8e67a952-9e23-4f23-8e0a-8d6dc4ef4f93 | DAYANARA BRIONES | Nicole
35 | 2023-07-24 | Remote | ECU0195 | ef53156b-0121-4ea4-9668-5ce0771d8767 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0195 | 0c542a3f-b89e-4bb4-8f87-2b12b92e93be | DANIEL TENELEMA | Nicole
36 | 2023-07-24 | Remote | ECU0196 | 6b0fc600-70d7-40aa-a5a7-611a2926d2b6 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU0196 | 26d4712f-9927-4181-8511-4cd1fa6a8450 | DANIEL TENELEMA | Nicole
37 | 2023-07-24 | Remote | ECU02026 | e856805d-d3e8-4b0a-a7e4-e82ceca26f49 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU02026 | d99c3b1a-52da-40e7-8d24-5f336ff607ec | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU02026 | 5af5e02a-e479-4e58-a88f-d7f52ce1eb39 | DAYANARA BRIONES | Nicole
38 | 2023-07-24 | Remote | ECU0203 | 60b404cf-aceb-452a-ab25-536c4e6599b8 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0203 | 77fd449d-61d4-45b7-87ce-31305479f1da | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0203 | 5e34e4a3-70b2-48b5-a8f3-a5bf63ba17e1 | DANIEL TENELEMA | Nicole
39 | 2023-07-24 | Remote | ECU0204 | 0daccdb4-fbde-4a53-b075-841b827392ca | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0204 | a1db9794-c8f5-4d62-906f-8979aa55a5c2 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0204 | 49fe3dfb-030f-4106-a16d-12cb6370add0 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0204 | 40058476-dbd1-4784-b765-bfcb0dbe9887 | STEPHANIE RAMOS | Nicole
40 | 2023-07-24 | Remote | ECU0206 | 0edcd4f4-8594-448f-95d8-cab39fbc4a43 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0206 | 30775b37-bc21-471d-9fbf-59860df7d185 | STEPHANIE RAMOS | Nicole
41 | 2023-07-24 | Remote | ECU0223 | af598970-de29-427d-8d30-48460c199475 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0223 | 8aae6694-dc33-4b83-9d1d-a091d4828d22 | DAYANARA BRIONES | Nicole
42 | 2023-07-24 | Remote | ECU0260 | afb1e7ab-43ea-4584-b221-6613b078f207 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0260 | c28ee94d-9059-43e5-bdbb-c01f60c9d1a3 | MARCELO CARDOSO | Nicole
43 | 2023-07-24 | Remote | ECU0273 | 1275da75-e5d6-41fd-84a9-ae572d48f7cc | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0273 | ec1f5420-23b8-4362-b0f3-7d0e04ee43de | DAYANARA BRIONES | Nicole
44 | 2023-07-24 | Remote | ECU0277 | 19336eeb-5ec9-47cc-bd3b-ca61076a2f9c | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0277 | 185e6e29-ec20-42c3-8d14-8e459d3a9e71 | STEPHANIE RAMOS | Nicole
45 | 2023-07-24 | Remote | ECU0280 | dcedfa9d-f6cd-417d-b343-1056542bfc24 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0280 | b5593bb9-a799-4dca-98b5-ee320288046a | KATHERINE BALAREZO | Nicole
46 | 2023-07-24 | Remote | ECU0281 | 4c63b915-ff96-426d-97d1-3084224beed6 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0281 | d9df7653-4f50-43a0-9c16-464c03235dee | KATHERINE BALAREZO | Nicole
47 | 2023-07-24 | Remote | ECU0285 | 9024143f-7ede-468b-ae19-7a1352f33d41 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0285 | 0261bd5a-9764-4a4f-a4b7-8c148b1c0e0a | KATHERINE BALAREZO | Nicole
48 | 2023-07-24 | Remote | ECU0292 | 75c3f243-7f28-40fa-b833-384c523ceddb | MARCELO CARDOSO | Nicole
| 2023-07-24 |  | ECU0292 | 2dadb222-6e08-496b-888b-a53cfdda9fc2 | STEPHANIE RAMOS | Nicole
49 | 2023-07-24 | Remote | ECU0297 | 1772153d-3e89-4c71-82aa-3495e971892c | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0297 | e35911a3-3027-4195-8a01-d6bad41c6e50 | MARCELO CARDOSO | Nicole
50 | 2023-07-24 | Remote | ECU0299 | a3e7c6cf-f147-4df1-9da6-43b7a44c3899 | MARCELO CARDOSO | Nicole
| 2023-07-24 |  | ECU0299 | b854b60d-b014-441d-8748-28cf24bee452 | STEPHANIE RAMOS | Nicole
51 | 2023-07-24 | Remote | ECU03026 | 541beaf8-8822-4649-93cc-ffb5770c9f5b | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU03026 | d8c04180-ccc8-4d36-82e2-4ceee3d746ac | STEPHANIE RAMOS | Nicole
52 | 2023-07-24 | Remote | ECU03034 | 422c7b84-36f9-4343-adf4-167f0855be70 | DANIEL TENELEMA | Nicole
| 2023-07-24 |  | ECU03034 | f8473b6b-a3d5-48b2-acbb-19f96afd1745 | KATHERINE BALAREZO | Nicole
53 | 2023-07-24 | Remote | ECU0306 | acf3e667-2ab5-4190-be66-cfeaad7d8647 | MELISSA MERA | Nicole
| 2023-07-24 |  | ECU0306 | ef412da3-15b9-4b11-b9a2-61235e11fac0 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0306 | 85195c11-14e7-43c3-8565-42a778d58802 | MELISSA MERA | Nicole
54 | 2023-07-24 | Remote | ECU0310 | 92555f1c-e316-4568-b0b0-035fbbf9cd4c | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU0310 | 405adea7-472c-41be-86b0-f6d071877640 | KATHERINE BALAREZO | Nicole
55 | 2023-07-24 | Remote | ECU0312 | ff043db2-8f16-48ea-9353-20d1daf0835f | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0312 | 704720c9-d3f2-4a5d-b9c0-556cfe5b0b02 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0312 | 0217e135-df4f-4f2f-9bbb-9af874355fe3 | MELISSA MERA | Nicole
56 | 2023-07-24 | Remote | ECU0314 | 048b0426-2fd3-4cea-818b-5857a161ce35 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0314 | 061e619c-9626-4ab5-b08a-505aadd495fc | DANIEL TENELEMA | Nicole
57 | 2023-07-24 | Remote | ECU03161 | 51860d96-2eeb-4d98-9328-ce420642bcc6 | MELISSA MERA | Nicole
| 2023-07-24 |  | ECU03161 | 3cabe55e-d0ff-4d83-83bf-a14b16c5571f | KATHERINE BALAREZO | Nicole
58 | 2023-07-24 | Remote | ECU0320 | 322ba242-63fc-4ddb-9fb1-b1f351473649 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0320 | 84deafbb-1ab4-4778-8252-800adbf3e69e | KATHERINE BALAREZO | Nicole
59 | 2023-07-24 | Remote | ECU0322 | 206d95a1-bbf6-454a-b62c-5ce4edbd8a49 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0322 | b154ffe5-d134-4f21-ba9b-3971a0cd546b | KATHERINE BALAREZO | Nicole
60 | 2023-07-24 | Remote | ECU0323 | f75e68a2-0e82-4cdd-80ae-6b9b9f84974f | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0323 | 117c50b9-718a-4a61-b4d0-a966c4dbc79f | KATHERINE BALAREZO | Nicole
61 | 2023-07-24 | Remote | ECU0324 | b1ebb9aa-7146-4039-98ff-9a25a12e9b51 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0324 | 1d253cb4-a16a-4ae8-96c9-c1129e0ddbe5 | KATHERINE BALAREZO | Nicole
62 | 2023-07-24 | Remote | ECU0325 | 979f3057-98ad-4e3e-8a0e-4de2af139e20 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0325 | 735f6901-f32e-4a72-9358-201729fa0acb | KATHERINE BALAREZO | Nicole
63 | 2023-07-24 | Remote | ECU0327 | bc6a1e35-02df-47e1-a931-a20faba626bd | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0327 | c1ff284b-da43-45fc-a4b9-ec8487b08c41 | ANTONY VEGA | Nicole
64 | 2023-07-24 | Remote | ECU0329 | 2cd8fbfc-5898-4bb4-91a1-c891f6707c82 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0329 | 45263464-f11b-48e0-ba51-1973be133912 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0329 | 90fada10-23b4-4bc0-b7d8-3d7665ac0084 | KATHERINE BALAREZO | Nicole
65 | 2023-07-24 | Remote | ECU0394 | dba6999c-a826-4fd3-9300-d388a76cb943 | DAYANARA BRIONES | Nicole
| 2023-07-24 |  | ECU0394 | 64780aaf-0e33-44de-a414-868454a802d8 | ANTONY VEGA | Nicole
66 | 2023-07-24 | Remote | ECU0404 | afd40bf1-ac3e-445a-baf9-2d66808dd31e | MELISSA MERA | Nicole
| 2023-07-24 |  | ECU0404 | a07be561-1651-473c-88ae-01384f2ce3a1 | MELISSA MERA | Nicole
67 | 2023-07-24 | Remote | ECU0451 | bf30bfd5-a927-4fec-a037-5a8e11c8bc99 | KATHERINE BALAREZO | Nicole
| 2023-07-24 |  | ECU0451 | ce25bb65-a55f-4682-a3e7-3f185de3b7a4 | KATHERINE BALAREZO | Nicole
68 | 2023-07-24 | Remote | ECU10984 | d36a2646-9a0a-4ab7-93a5-b93dbe962ee9 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU10984 | c6d844a7-abbc-47c7-8661-928306e408d3 | MARCELO CARDOSO | Nicole
69 | 2023-07-24 | Remote | ECU10986 | 30c34d8c-eea7-4aae-ab6f-84c6485deab3 | STEPHANIE RAMOS | Nicole
| 2023-07-24 |  | ECU10986 | 975dac47-1fce-4a47-956a-6ab3502d9c73 | MARCELO CARDOSO | Nicole
70 | 2023-07-24 | Remote | ECU21000 | 30851617-e130-44ca-8461-4a7ae4cac238 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU21000 | 3a5119f3-abd5-485e-b111-04737d49b62a | ANTONY VEGA | Nicole
71 | 2023-07-24 | Remote | ECU21062 | ef859e15-9acf-49a4-a1cd-37b1876baf72 | ANTONY VEGA | Nicole
| 2023-07-24 |  | ECU21062 | da89a425-00c5-4ddf-8307-2c4f3b55cfe1 | MELISSA MERA | Nicole

## Sample
| F2F |  |  | Remote
| Phase 1 | Phase 2 | Total | Phase 1 | Phase 2 | Total
Raw Download |  |  | 841 |  |  | 2395
Unique HHID |  |  | 816 |  |  | 1024
Final Complete HHID before Dedup |  |  | 760 |  |  | 615
Current Final Complete |  |  | 749 |  |  | 555

## Error Log
No | Date | Modality | HHID | uuid | Enumerator | Logged by: | Comments | Action Required | Other comments | Action Taken | Closed?
1 | 2023-06-20 | Both | General |  |  | Nicole | For remote surveys, we have 130+ submissions but only 36 completed surveys. | We need to discuss a consistent calling protocol and the way we record final call outcomes and what to submit to the server. |  | Only effective calls / visits are registered in MoDA, NUMMA maintains a separate register of calls / visits made to facilitate data cleaning
2 | 2023-06-20 | Both | General |  |  | Nicole | In LCS sections, the LcsEN_crisis_HealthEdu and Lcs_crisis_HealthEdu are in the current dataset. However, we removed the education part since Myanmar. | Please confirm if this is a fail to update or on purpose. If we need to update them, please record the form version so we can flag the responses before and after the change. | Updated by removing the EN or changing the question? I didn't see it in the dataset
3 | 2023-06-20 | Remote | General |  |  | Nicole | In remote LCS, LcsEN_em_ChildWork is in the current dataset. However, the question asked about Food and we already corrected this in Myanmar to Lcs_em_ChildWork | Please confirm if this is a fail to update or on purpose. Currently Nicole renamed it coz this seems like a simple naming typo.
4 | 2023-06-20 | F2F | General |  |  | Nicole | I noticed that RespAge was removed from the main survey in F2F (now it's only in the roster). Ideally, we still get the same information FROM the roster. However, since we do not have a proper constraint on how many people can be marked as Respondent in the roster. Now there are 10 households with more than 1 member marked as respondent, head of household. Then we have to follow up one by one to make sure we know the basic characteristics of the respondent and head of household. | Team to discuss
5 | 2023-06-24 | F2F | ECU010224 | f158bc74-4d08-479b-96dd-23787d3880af | VÍCTOR FLORES | Nicole | This hhid is duplicated by two enumerators which should not be the case. This was discovered during the field visit and reported to Maria and the team. The enumerators involved were to visit the households again and do the interviews else should be deleted from the data | To call back the identified hh to confirm if interview took place and to send the enumerators back to the field
|  |  |  | d2012955-cf1e-48ee-bdda-4d8dce28d5ee | JOSSELYN TENELEMA | Nicole
6 | 2023-07-07 | F2F | ECU020144 | 614448c3-4f46-4a7a-b9e7-0843e1031cc4 | JEFFERSON TENORIO | Nicole | This hhid is duplicated by two enumerators which should not be the case. This was discovered during the field visit and reported to Maria and the team. The enumerators involved were to visit the households again and do the interviews else should be deleted from the data | To call back the identified hh to confirm if interview took place and to send the enumerators back to the field
|  |  |  | 94b12b58-099c-490a-a338-38fe94c0872a | ERICK GUERRA | Nicole
7 | 2023-07-07 | F2F | ECU020160 | 00f31eb6-282f-4aaa-88e9-2ca5bf8fcfb3 | JEFFERSON TENORIO | Nicole | This hhid is duplicated by two enumerators which should not be the case. This was discovered during the field visit and reported to Maria and the team. The enumerators involved were to visit the households again and do the interviews else should be deleted from the data | To call back the identified hh to confirm if interview took place and to send the enumerators back to the field
|  |  |  | 2376096a-ae83-4465-b38c-62aa25017bd5 | ERICK GUERRA | Nicole
8 | 2023-07-07 | F2F | ECU0212373 | d7b33ab9-df1a-43f2-8717-8ad502ff11ce | ERICK GUERRA | Nicole | This hhid is duplicated by two enumerators which should not be the case. This was discovered during the field visit and reported to Maria and the team. The enumerators involved were to visit the households again and do the interviews else should be deleted from the data | To call back the identified hh to confirm if interview took place and to send the enumerators back to the field
|  |  |  | 5199b75b-7cd6-4986-921d-15cb5909c0e3 | JEFFERSON TENORIO | Nicole
9 | 2023-07-07 | F2F | ECU0312397 | cc38c82a-8439-472b-9145-4479a306f7c5 | VERÓNICA GUERRERO | Nicole | Duplicated ID
|  |  |  | 8635e577-28dc-445f-9379-c2df9c503119 | VERÓNICA GUERRERO | Nicole
10 | 2023-07-07 | Remote |  | f762f176-7368-4ade-930c-3d246f4a9d4d | DAYANARA BRIONES | Nicole | Completed but no HHID - How is this even possible? | Look into the specific response and check with the enumerator
11 | 2023-07-07 | Remote |  | 1de2d9cd-18ba-4721-a45e-d4d6c814cb3c | ANTONY VEGA | Nicole | Not completed - but no HHID, we should avoid this! | Look into the specific response and check with the enumerator
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Simon @Alirah please add the final calling protocol here on what has been done
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alirah Reply: the forms were finally updated so no need for versions
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Alirah Reply: Failure to update. Since we did not edit this in the final form
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alirah Please confirm so I close the case Reply: I guess the generic english form was not updated.
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alirah @Cassandra @Simon Reply: The age of respondent has been updated in the current version. Should reflect in today's submissions Reply: @Nicole WU please filter those 10hh for the team to follow up on why there are multiple HH heads/respondents
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Simon HERTELEER please follow up with Maria and the team to clarify and correct these duplicates both in the f2f. They should cross check the names with the actual HHIDs given in the excel sheet