## Sheet1
Phase | Activity | Responsibility
Preparation | Participate in a training of trainers, in order to be able to conduct the trainings and roll-out of this activity in the field | RAM from RBs (RBD & RBP) HQ – RAM-N & RAM-H
Preparation | Develop a dashboard for rapid data verification using Tableau | RAM-N (Nicole, with the support of Alessandra)
Preparation | Design a standardized survey instrument (questionnaire) template in EnglishWFP will also design and program the questionnaire into ODK-based formats like MoDA. | HQ – RAM (Isra?)
Preparation | Standardized training materials explaining the study will be provided to be adapted to the country context? | HQ – RAM (Alirah?)
Preparation | Share the survey instruments and training materials with the RBs and COs for translation. | HQ – RAM (Alirah?)
Preparation | Ensure the translation and back translation of the questionnaire & training package into local language(s) relevant to the selected area, to be reviewed and contextualised by the WFP/CO. | RAM from RBs (RBD & RBP)
Preparation | Contract a service provider to conduct the data collection. Work with them to develop a budget and timeframe (in collaboration with RAM-N). Provide the necessary logistics (including but not limited to stationery, tablets, other field logistics for the enumerators). | CO -> Service provider (ICASEES)
Preparation | Recruit the relevant on- and off-field enumerators to conduct the F2F and Phone interviews. | Service provider (ICASEES)
Recruit supervisors to supervise the field and remote data collection for data quality
Preparation | Apply for and arrange for permits to enter and conduct household surveys in study areas identified in conjunction with CO | ??
Preparation | Identify, and randomly select households to be interviewed for the study in Central African Republic. | CO RAM ?
Preparation | Random assignment of the households into two groups (A and B) | HQ - RAM-N (Alirah)
Preparation | Making the initial contact with selected households to arrange the interview (both F2F and phone-based). | are we doing this??
Training | Provide the venue for the training of enumerators including the food, drinks (water) and coffee breaks, as well as all technical facilities like laptops, projectors, white board, and necessary stationery. Provide transportation for the enumerator field visit during questionnaire testing NB: CO to provide tablets or smartphones. | Service provider (ICASEES)
Training | Lead the field training (both F2F and remote) in collaboration with WFP RAM teams (RAM-N and RAM-H). | RBD & CO RAM
Training | Test the final Questionnaire & provide feedback for adjustments of the questionnaire after testing if necessary. Identify specific questions after field testing of questionnaire to be adjusted providing the correct wording or phrase(s) to reflect country specific nuances | CO & Service provider (ICASEES)
Training | Adjust the questionnaire in XLSForm after testing if necessary. | HQ – RAM-N (Cassandra, with the support of Isra and Nicole, as necessary)
Data collection | Provide logistics required for the field survey. Ensure that the data is sent to the server on a daily basis for verification by WFP RAM teams, ensuring data privacy for all respondents during data collection, storage, and data transfers to WFP. | Service provider (ICASEES)
Data collection | Carry out verifications of data quality on the server using the Tableau platform and data downloaded by Moda, | HQ – RAM-N (Nicole)
Data collection | Carry out data quality assurance and ensure that checks are put in place for incoming data from the field with poor data quality compensated in required samples. Communicate regularly with RAM-N HQ (Nicole) to feedback any data quality issues during the data collection in the field. | HQ – RAM-N (Cassandra)
Data cleaning | Code and enter all responses for open-ended questions in both F2F and Phone-based interviews. | ??
Data cleaning | Provide translated versions of any data collected during the survey that has not been pre-translated into English. | CO??
Data cleaning | Clean, and submit the final dataset in English using standard WFP variable names in SPSS or Stata formats. | CO??
Data analysis and reporting | Final report at the end of the survey and data processing. Provide an end line report detailing the sampling, weights, and any syntax used for the data aggregation if any to WFP. The final report will provide the initial statistics of the composition of respondents, their distribution. | HQ – RAM-N (Alirah) - is it necessary for the SP to also produce a final report?