# SCOPE of WORK (SoW) for rCARI VALIDATION STUDY IN CENTRAL AFRICAN REPUBLIC

# STUDY BACKGROUND

Food insecurity is a multidimensional concept, which requires use of multiple indicators for analysis of the different dimensions. Several methods have been developed to measure the magnitude and severity of acute food insecurity over time. The humanitarian actors are facing an increasingly challenging situation as the food needs have been dramatically increasing in recent years. In 2021, at least 193 million people in 55 countries/territories were acutely food insecure (IPC/CH Phase 3 or above), an increase of around 40 million people from 2020 (Global Report on Food Crises 2022). Similarly, based on available data from 82 countries where WFP has operational presence, it is estimated that around 345 million people will be acutely food insecure adjusting for the increase war in Ukraine, climate change shocks, and rising inflation coupled with the global economic downturn (Global Operational Response Plan, 2022).

Although different methodologies currently exist to assess and report food insecurity, the level of acceptance and reliance by different stakeholders depend on how transparent, compatible, and comparable the results are. In 2012, WFP adopted the Consolidated Approach for Reporting Indicators of Food Security (CARI) as a standard food security measurement methodology, for household-level profiling, targeting, and prioritization of people in need of assistance. The guidelines for CARI have since 2012 evolved with adjustments to show the aggregation procedure.

The 3rd Edition of the CARI guidelines (CARI.v3), published in December 2021, included several methodological novelties, and indicators to capture more food security and economic related variables to better measure acute food insecurity. In addition, the onset of the COVID-19 pandemic brought to the fore new challenges to traditional data collection methods with movement restrictions. WFP developed the remote CARI (rCARI) as a proxy for the original face-to-face CARI methodology to fill data gap created by the Covid-19 associated lockdowns. rCARI presents practicality in the measurement of food security in emergencies where quick operational decisions are needed, and traditional F2F methods like CARI. This is evidenced in it use during the height of the COVID-19 pandemic and the heavy-armed conflict ongoing in Ukraine to assess, and report food security and other humanitarian crises.

However, to date, rCARI has not been empirically validated against the traditional F2F CARI (CARI. V3) to assess the compatibility or otherwise of the two modules. Validating the rCARI is thus a major step in the process of bridging a critical grey area of reporting food insecurity reporting that arises because of lack of data in emergencies.

At this time, WFP-HQ would like to hire the services of a Service Provider that will conduct field study to validate rCARI methodology through household and phone interviews.

# OBJECTIVE/PURPOSE OF THE STUDY

Thus, the main objective is to validate the rCARI methodology using a randomized controlled cross over design (details outlined in the methodology section) where each household will be interviewed twice (one F2F and one phone-based interview).

It is against this backdrop that WFP Central African Republic wishes to contract a Research Service Provider(s), with capacity to conduct fast and cost effective Face-to-Face (F2F) interviews and remote phone-based interviews for approximately 600 households in 20 Admin3 areas that will spread across two regions (CO to enter the names of region(s)/geographical area(s)).

The survey is to be implemented as a crossover design (details outlined in the methodology section) where each household will be interviewed twice (one F2F and one phone-based interview).

# STUDY METHODOLOGY

The Service Provider will collect primary data at the household, using both remote and face-to-face methods involving total of 600 households randomly selected from a minimum of two livelihood areas or regions preferably from the South and North of the country, and 20 Admin3 area (villages). Each household will be interviewed twice through F2F and phone-based interviews using a crossover design (see Figure 1). A total of 1200 interviews will be conducted (600 face to face and 600 phone interviews). In general, the interview will collect data on household and respondent demographics, livelihoods, expenditure, food security indicator variables (calorie intake based on a stated recall period) and assets (see attached the full questionnaire).

Group B (F2F interview)

Group A (Phone interview)

From each PSU, 30 households will be randomly selected.

Final sampled households will be randomized into two groups, i.e., survey Group A (300 households) and survey Group B (300 households). The interviews will be conducted in two phases to accommodate the cross-over design methodology.

Sampled Households

Central African Republic

Admin2 Districts

Livelihood zones/Admin1 regions

Admin4

Villages/Communities

Simple random sampling to select at least 2 regions /livelihood zones based on the food security situation

Based on the number of regions selected, draw a list of      districts from the selected regions and randomly select 4 districts.

In the same manner, list smallest administrative units within the country (e.g., villages) and randomly select 20 ADMIN4 Units as Primary Sampling Units (PSU)

In the first phase, both Groups, A and B will be interviewed through Phone-based modules. In the second phase, both Groups, A and B will then be interviewed using F2F modules (i.e., each household head will be interviewed twice).

Group B (Phone interview)

Group A (F2F interview)

Figure 1: Sampling and selection of data unit decision tree

# DESCRIPTION OF SERVICES AND TASKS

A standardized survey instrument (questionnaire) template designed by WFP in English as an online form will be provide for the study. WFP will also design and program the questionnaire into ODK-based formats like MoDA.

The Service Provider is expected to provide the following services under the broad areas categorized above within the time of engagement with WFP:

- Translation and Finalization of the Questionnaire

- Initial translation and back translation of the questionnaire into local language(s) relevant to the selected area and English respectively to be reviewed by WFP/CO.

- Test the final Questionnaire.

- Provide feedback for adjustments of the questionnaire after testing if necessary.

- Identify specific questions after field testing of questionnaire to be adjusted providing the correct wording or phrase(s) to reflect country specific nuances

- Recruitment and training of staff

- Recruit the relevant on- and off-field enumerators to conduct the F2F and Phone interviews. Enumerators should be qualified and good understand of the local conditions and terrain of the study areas delivered (Minimum requirement for enumerators is an Undergraduate Degree).

- Recruit supervisors to supervise the field and remote data collection for data quality

- Provide field training in collaboration with WFP RAM team

- Provision of Logistics

- Provide the necessary logistics (including but not limited to stationery, tablets, other field logistics for the enumerators).

- Provide logistics required for the field survey.

- Providing venues for training of enumerators including the food, drinks (water) and coffee breaks, as well as all technical facilities like laptops, projectors, white board, and necessary stationery.

- Provide transportation for enumerator field visit during questionnaire testing and F2F survey.

- Provide a low-budget mobile phone to around 600 household heads for the purpose of phone-based interviews.

- Data Collection, Preparation, and Transmission

- Identify, and randomly select households to be interviewed for the study in Central African Republic.

- Random assignment of the households into two groups (A and B)

- Apply and arrange for permits to enter and conduct household surveys in study areas identified in conjunction with CO

- Making the initial contact with selected households to arrange the interview (both F2F and phone-based).

- Code and enter all responses for open-ended questions in both F2F and Phone-based interviews.

- Provide translated version of any data collected during the survey that has not been pre-translated into English.

- Clean, and submit the final dataset in English using standard WFP variable names in SPSS or Stata formats.

- Ensure data privacy for all respondents during data collection, storage, and data transfers to WFP.

- Ensure data quality assurance and checks are put in place for incoming data from the field with poor data quality compensated in required samples

- Ensure a smooth transfer and or linking of final survey data to WFP servers.

- Give WFP access to monitor real-time data collection

- Report

- Provide an end line report detailing the sampling, weights, and any syntax used for the data aggregation if any to WFP.

- The final report will provide the initial statistics of the composition of respondents, their distribution.

# DELIVERABLES

The Service Provider shall be requested to deliver the following according to the planned timelines:

- List of locations, names, and number of households per admin level with actual mobile penetration.

- List of households selected with contact details and locations.

- Translated finalized questionnaire ready for both F2F and Phone-based surveys.

- Cleaned dataset in English using standard WFP variable names for both F2F and Remote surveys at the household and individual levels respectively.

- All opened ended answers are either coded, aligned to existing variables or translated (into English) and coded into the main data file.

- Final report at the end of the survey and data processing.

# TENTATIVE TIMELINE AND KEY MILESTONES

| Time Activity | Nov 2022 |  | Dec 2022 |  |  |  |  | Jan 2023 |  |  |  |  | Feb 2023 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | W1 | W2 |  | W3 | W4 | W5 | W6 |  | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |
| - Translation of Questionnaire |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Liaise for Permits from Local Gov’t/ Authorities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Recruitment of Enumerators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Training of Enumerators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Testing of Questionnaire |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Compiling sampled households contacts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Data Collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Data Entry & Cleaning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Final Dataset & Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Note: W = Week

# ADMINSTRATION AND REPORTING

The Service Provider will be required to give a weekly report on the progress of work particularly during the hiring, acquisition of relevant permits and translation of questionnaires. During the proper interview/survey phase (i.e., from the 3rd week to 12th week), these reports may be required on daily or bi-weekly bases as data is transferred. These shall contain information such as number of interviews successfully completed, refusals if any indicating reasons for refusal, any technical or operational challenges encountered, and any other information considered directly or indirectly relevant to the successful implementation of the survey.

For the purposes of this study, supervision, communications (enquiries and reports) and management will be directly under RAM-HQ in Rome. The focal person for all communications will be Alirah Weyori (alirah.weyori@wfp.org) copying Mohamed Salem (Mohamed.salem@wfp.org).

# GLOSSARY AND DEFINITION OF TERMS

CARI			Consolidated Approach for Reporting food Insecurity

CO			Country Office

ECMEN			Economic Capacity to Meet Essential Needs

F2F			Face-to-Face

FCS			Food Consumption Score

FES			Food Expenditure Share

H/A			Height for Age

HDDS			Household Dietary Diversity Score

HHS			Household Hunger Score

HQ			Headquarters

LCS			Livelihood Coping Strategies

LCS-EN			Livelihood Coping Strategy-Essential Needs

MADD			Minimum Acceptable Diet

MDDW			Minimum Dietary Diversity for Women

MEB			Minimum Expenditure Basket

MoDA			Mobile Operation for Data Acquisition

MUAC			Mid-Upper Arm Circumference

ODK			Open Data Kit

RAM			Research Assessment and Monitoring

rCARI			Remote Consolidated Approach for Reporting food Insecurity

rCSI			Reduced Coping Strategy Index

SPSS			Statistical Package for Social Scientist

W/A			Weight for Age

WFP			World Food Programme

WGQ			Washington Group Questions

WI			Wealth Index

- Food consumption score (FCS) - The Food Consumption Score (FCS) is the most used food security indicator by WFP and partners. This indicator is a composite score based on households’ dietary diversity, food frequency, and relative nutritional importance of different food groups. The FCS is calculated by inspecting how often households consume food items from the different food groups during a 7-day reference period.  In addition to this, the FCS module collects data on sources of the consumed foods acquired by households.

- Reduced Coping Strategy Index (rCSI) - is an indicator used to compare the hardship faced by households due to shortage of food. The index measures the frequency and severity of the food consumption behaviors the households had to engage in due to food shortage in the 7 days prior to the survey.

- Livelihood Coping Strategies - Essential Needs (LCS-EN) is an indicator used to understand the medium and longer-term coping capacity of households and their ability to overcome challenges in meeting their essential needs in the future.

- Economic Capacity to Meet Essential Needs (ECMEN) - The ECMEN indicator identifies the percentage of households whose expenditures exceeds the Minimum Expenditure Basket (MEB).

- Minimum Expenditure Basket (MEB) - The MEB is defined as what a household requires to meet their essential needs, on a regular or seasonal basis, and its cost. The MEB covers those needs that households meet fully or partially through the market.

- Food Expenditure Share (FES) - Is an indicator used to measure households’ economic vulnerability. It determines the economic vulnerability without the need of having reference to a poverty line or minimum expenditure basket.

  - Expenditure on food items (30-day recall)

  - Expenditures on non-food items (30-day recall)

  - Non-food items (six-month recall

- Household Hunger Score (HHS) - The Household Hunger Scale (HHS) is a simple indicator used to measure household hunger within food-insecure areas. It has been developed and validated for cross-cultural use.

- Household Dietary Diversity Score (HDDS) & Dietary Diversity at the individual level - The HDDS aims to reflect the economic ability of households to access a variety of foods​. The data for this indicator is based on households’ self-reporting of the 12 food groups consumed in the previous 24hours​.

- Dietary energy intake (kcal/capita/day) - An indicator calculated either at the household or individual level that serves as an estimate of calories of food available for consumption. This indicator does not give indication on affordability, access, or consumption of dietary energy by different households within a given location, which means that sufficient supply does not ensure sufficient dietary energy consumption by nutritionally vulnerable groups.

- Minimum Acceptable Diet (MAD) - Minimum Acceptable Diet (MAD) is a proxy indicator used to assess the nutrient density of young children’s diet. An internationally validated Infant and Young Child Feeding (IYCF) indicator, MAD measures the proportion of children 6-23 months who consumed a minimum acceptable diet (outside breast milk consumption) in the past 24 hours.

- Minimum Dietary Diversity for Women (MDD-W) - is a proxy indicator which assesses population -level micronutrient adequacy, an important dimension of diet quality, for women’s diets. The indicator measures the proportion of women 15 - 49 years who have achieved minimum dietary diversity (i.e., met the threshold of five or more groups out of the ten defined food groups) in the past 24 hours.

- Weight & height for age z-scores (W/H for age z-score) – These are anthropometric measures used to gauge malnutrition amongst children between the ages of 6months and 5years (stunting and wasting).

- Mid Upper Arm Circumference (MUAC) – The indicator measures the circumference of the mid upper arm of children between 6 months and 5 years who have malnutrition (wasting or thinness) and are at risk of dying. The indicator is measured using a standardized three colored tape (red, yellow, and green) with each color indicating different level of food insecurity or malnutrition.

- Wealth index (WI) - The wealth index (WI) is a composite index composed of key asset ownership variables; it is used as a proxy indicator for household wealth and thus the households’ ability to cope with shocks that leave it vulnerability to poverty and or food insecurity.

- Disability (WG Short Set of Questions – WGQ-SS) - These are 6 standard questions relating to mobility, seeing, hearing, cognition, communication, and self-care of the respondent. This measure helps to assess and quantify the relationship between disability and food security in each context to reflect in the design of WFP activities over time.

# RELEVANT DOCUMENTATION

- Consolidated Approach for Reporting Indicators of Food Security (CARI) Guidelines - Third edition

- Consolidated Approach for Reporting Indicators of Food Security (CARI) Guidelines - Second edition

- CARI & IPC Factsheet: Technical Annex