## Planning rCARI
Activity | Number of days | July |  |  |  | August |  |  |  | Deadline/status | Responsible | Commentaires
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Village sampling (Admin 5) | - | [8 empty] | Done | CO(KABRE Moumouni) | bar: July 1
Recruitment of interviewers (TPM) | 3 | [8 empty] | 2023-07-07 | CO(KABRE Moumouni) | bar: July 1 to July 2
Design of census questionnaire | 3 | [8 empty] | 2023-07-07 | CO(Moro DABRE, KABRE Moumouni) | deja developpe par Alirah - il va le partager avec vous | bar: July 2
Briefing of enumerators | 1 | [8 empty] | 2023-07-07 | CO(KABRE Moumouni, Faroukou GARBA) | a voir les dates en generale - est-ce qu'ils sont correctes? | bar: July 2
Data collection for household census | 5 | [8 empty] | 2023-07-15 | Enquêteurs (TPM) | bar: July 2 to July 3
Processing and cleaning of census data | 2 | [8 empty] | 2023-07-18 | CO(KABRE Moumouni) | bar: July 3
Sampling at Household level | 1 | [8 empty] | 2023-07-19 | CO(KABRE Moumouni, Faroukou GARBA) | le role d'Alirah | bar: July 3
Training of staff (TPM et Call Center) | 3 | [8 empty] | 2023-07-24 | Faroukou and Alirah | 4 jours de formation - et 2 a part - un pour le parti F2F & un pour le parti remote; CARE - gender assessment | bar: July 4
Field data collect for rCARI | 7 | [8 empty] | 2023-07-31 | Call Center and TPM | bar: July 4
Data processing | 4 | [8 empty] | 2023-08-07 | CO(KABRE Moumouni) | le role du siege | bar: August 1
rCARI data collection workshop | 1 | [8 empty] | 2023-08-10 | WFP , Call Center , TPM | pourquoi? | bar: August 1 to August 2
Data analysis | 3 | [8 empty] | 2023-08-17 | Faroukou and Alirah | le role du siege | bar: August 2 to August 3
Reporting | 5 | [8 empty] | 2023-08-26 | Faroukou and Alirah | le role du siege | bar: August 4
Sharing report/dissimination | 1 | [8 empty] | 2023-08-27 | CO and HQ | le role du siege | bar: August 4
Gender from CO Burkina Faso
Si oui, on va partager l'info (villages, timeline)
MOU - TPM National NGO - F2F
Call Center ADECONTACT? - remote (since 2020) - CFM, mVAM, FSOM, mPDMs - recording & transcription
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: contextualisation of the census questionnaire

## Budget of rCARI
Activités | Unités | Quantité | Jours/unites | PU | Montant | Amount in USD | Commentaires
Listing |  |  |  |  | 0 | 0
Brefing sur la technique de recensement des ménages | Pause café | 5 |  | 7000 | 35000 | 59.322
Contrat ONG (le meme pour le F2F) pour le recensement | H/J | 10 | 7 | 70000 | 4900000 | 8305.0847 | nous ne payons pas strictement pour les contrats non? nous payons pour les activites et puis 7%? 10 enqueteurs, 7 jours; montant a revoir... (70000 -> ou 60000)
Location Motos et carburant | Jours de location | 10 | 7 | 35000 | 2450000 | 4152.5424 | 70 enqueteurs? 70 jours?
Formation technique sur rCARI |  |  |  |  | 0 | 0 | 2 formations 1) remote, 2) F2F - il faut inclure: d'eau, location salle, transport pour le pre-test, fournitures et equipements - separate budgets -
Perdiem participants | H/J | 100 |  | 45000 | 4500000 | 7627.1186
Transports participants | Transports | 20 |  | 20000 | 400000 | 677.9661
Pause café | Pause | 75 |  | 7000 | 525000 | 889.8305
Pause dejeuner | Dejeuner | 75 |  | 10000 | 750000 | 1271.1864
Collecte des données en Face à face | [6 empty] | veuillez fournir le budget dans 2 onglets: 1) remote, 2) F2F
Collecte des données rCARI | H/J | 70 |  | 70000 | 4900000 | 8305.0847 | combien des enqueteurs, superviseurs? frais de communication? montant a revoir... (70000 -> ou 60000) ; il faut voir le numero des enqueteurs et les jours necessaires
Location Motos et carburant | Jours | 70 |  | 35000 | 2450000 | 4152.5424
Collecte des données par téléphone
Collecte des données RCARI avec call center | Fiches | 600 |  | 8000 | 4800000 | 8135.5932 | il faut disaggrege: par paiements aux enqueuteurs (combien par personne), ajouter une superviseur pour le remote
Atelier de capitalisation sur les données | [6 empty] | enumerators (a travers les superviseurs doivent partager les lecons apprises chaque semaine) - ou en ligne?
Perdiem participants | H/J | 20 |  | 45000 | 900000 | 1525.4237
Transports participants | Transports | 20 |  | 20000 | 400000 | 677.9661
Pause café | Pause | 25 |  | 7000 | 175000 | 296.6102
Pause dejeuner | Dejeuner | 25 |  | 10000 | 250000 | 423.7288
Achat de smartphone complémentaire
Achat local de smartphone | unité | 10 |  | 220000 | 2200000 | 3728.8136 | 10 unites? pour USD 4000?- confirmed the smartphones (20 enumerators - smartphones may not be enough - 10 to be purchased)
Total |  |  |  |  | 29635000 | 50228.8136
est-ce qu'on peut ventiller enumerators et jours?