# SCOPE of WORK (SoW) for rCARI VALIDATION STUDY IN BURKINA FASO

# STUDY BACKGROUND

Food insecurity is a multidimensional concept, which requires use of multiple indicators for analysis of the different dimensions. Several methods have been developed to measure the magnitude and severity of acute food insecurity over time. Humanitarian actors are facing an increasingly challenging situation as the food needs have been dramatically increasing in recent years. In 2021, at least 193 million people in 55 countries/territories were acutely food insecure (IPC/CH Phase 3 or above), an increase of around 40 million people from 2020 (Global Report on Food Crises 2022). Similarly, based on data available from 82 countries where WFP has operational presence, it is estimated that around 345 million people will be acutely food insecure adjusting for the increase war in Ukraine, climate change shocks, and rising inflation coupled with the global economic downturn (Global Operational Response Plan, 2022).

Although different methodologies currently exist to assess and report food insecurity, the level of acceptance and reliance by different stakeholders depend on how transparent, compatible, and comparable the results are. In 2012, WFP adopted the Consolidated Approach for Reporting Indicators of Food Security (CARI) as a standard food security measurement methodology, for household-level profiling, targeting, and prioritization of people in need of assistance. The guidelines for CARI have since 2012 evolved with adjustments to show the aggregation procedure.

The 3rd Edition of the CARI guidelines (CARI.v3), published in December 2021, included several methodological novelties, and indicators to capture more food security and economic related variables to better measure acute food insecurity. In addition, the onset of the COVID-19 pandemic brought to the fore new challenges to traditional data collection methods with movement restrictions. WFP developed the remote CARI (rCARI) as a proxy for the original face-to-face CARI methodology to fill data gap created by the Covid-19 associated lockdowns. rCARI presents practicality in the measurement of food security in emergencies where quick operational decisions are needed, and traditional F2F methods like CARI. This is evidenced in its use during the height of the COVID-19 pandemic and the heavy-armed conflict ongoing in Ukraine to assess and report food security and other humanitarian crises.

However, to date, rCARI has not been empirically validated against the traditional F2F CARI (CARI. V3) to assess the compatibility or otherwise of the two modules. Validating the rCARI is thus a major step in the process of bridging a critical grey area of reporting food insecurity reporting that arises because of lack of data in emergencies.

It is in this context that WFP-HQ thus is preparing to engage the services of Service Providers (SP), namely ASSOCIATION MONDE RURAL (AMR) and ADKONTACT with the support of the CO, to conduct household surveys through both face-to-face and phone interviews, respectively.

# OBJECTIVE/PURPOSE OF THE STUDY

To validate the rCARI methodology through a survey experiment with stratified sample (details outlined in the methodology section).

# STUDY METHODOLOGY

The primary unit of analysis for this study is the household. It is against this backdrop that WFP Burkina Faso wishes to contract research service providers with the capacity to conduct fast and cost-effective face-to-face (F2F) interviews (Association Monde Rural - AMR) and remote phone-based interviews (ADKONTACT) for approximately 1400 completed interviews distributed across 40 Admin5/lowest Admin areas drawn and distributed evenly from two Admin1 regions (See Figure 1 for the design).

1) Centro Prefecture

2) North Prefecture

3) Plateau Central

The service providers will collect primary data from households, using both remote and face-to-face modalities. Households would be randomly sampled from a minimum of two Admin1 zones or prefectures in the Centre and the North of the country and distributed in 40 Admin5 zones (villages). The sampling frame will be pre-collected list of households (minimum of 100 households per Admin5 area) that will be compiled through a random walk method around each village, selecting every third house (with their consent taken to be potentially included into the study). In total, 4000 interviews will be conducted (2000 face-to-face and 2000 phone interviews using the same sample randomly assigned to each modality). Both interview modalities will collect data about household demographics, livelihoods, expenditure, food security variables and assets.

Association Monde Rural (AMR) will collect the primary data at the household level, using face-to-face methods involving total of 2000 randomly selected households. Meanwhile, ADKONTACT will collect the primary data at the household level, using remote methods (by phone).

  - SAMPLING FRAME

The actual study area selection will be based on phone network coverage, security (accessibility), and food security situation. Once the study areas have been selected (ADMIN1-ADMIN5), all households that live within each study area will form the sampling frame for the validation study. Households will be enlisted in a listing phase where trained enumerators will first visit the household seek their consent and collect baseline information (respondent and household characteristics) and contact information. Households listed that do not have phone contact information will be excluded from the final sample. This will ensure that only households with access to mobile phones are included in the study.

F2F Group

Remote Group

Collate a list at the villages and randomly select a minimum of 150 households per village. The final sampled households (3000) will be randomized into two groups, i.e., F2F Group and Remote Group (1500 households per group). The two groups would be interviewed simultaneously.

Based on the number of regions selected, draw a list of districts from the selected regions and randomly select 4 Communes. Equally distributed in the two Prefecture.

Sampled Households

Burkina Faso

Communes

Admin1/Prefectures

Admin5-Villages Villages/Communities

Two ADMIN1 Areas/regions (CENTRO & NORTH PREFECTURE) /livelihood zones based on the food security situation, accessibility, and phone coverage.

In the same manner, list all the villages within the selected communes and randomly select 20 villages as sampling clusters.

F2F Group will receive the CARI modules while remote Group will receive the rCARI modules.

Figure 1: Sampling and selection of data unit decision tree

# DESCRIPTION OF SERVICES AND TASKS

The role of WFP is to launch the study, and to provide the necessary materials and support from start to finish. This includes but is not limited to the following:

- Provide a standardized survey instrument (questionnaire) translated into French and programmed into ODK-based format for MoDA.

- Test the final questionnaire.

- Provide feedback for adjustments of the questionnaire after testing if necessary.

- Provide the necessary logistics and materials for the training (e.g., stationery, tablets, other field logistics for enumerators).

- Provide the final list of households selected with contact details and locations (built into the questionnaire), based on the listing exercise.

- Review and provide daily data quality checks of data sent to the server.

The Service Provider is expected to provide the following services under the broad areas categorized above within the time of engagement with WFP:

- Translation and Finalization of the Questionnaire

- Support the review and testing of the questionnaire during the training.

- Provide feedback for adjustments of the questionnaire after testing if necessary.

- Identify specific questions after field testing of questionnaire to be adjusted (providing the correct wording or phrase(s) to reflect country specific nuances).

- Recruitment and training of staff

- Provide enumerators to conduct the F2F and phone interviews, respectively. Enumerators must be qualified and have good understanding of the local terrain of the study areas.

- Provide supervisors for face-to-face and remote data monitoring for data quality.

- Ensure that all enumerators and supervisors are adequately trained by WFP.

- Provide the necessary materials (e.g., stationary).

- Provision of Logistics

- Provide logistics required for the field survey.

- Arrange transportation to field test the F2F questionnaire during the training.

- Listing and sampling

- Apply and arrange for permits to enter and conduct household surveys in study areas identified in conjunction with CO.

- Identify and compile a list of households to be used as the sampling frame for the study in Burkina Faso.

- At the same time, make the initial contact with these households to forewarn them that they may be selected for the interviews (both F2F and phone-based).

- Data Collection, Preparation, and Transmission

- Ensure data quality assurance and checks are put in place for incoming data from the field.

- Ensure data privacy for all respondents during data collection, storage, and data transfers to WFP.

- Send questionnaires to the server daily.

- Remote data collection

- Record phone interviews for quality checks.

- Clean, and submit the final transcripts for the recorded data in English (or French) (as well as the raw data).

- Report

- Provide a final report to WFP.

DELIVERABLES

The Service Providers will be requested to deliver the following according to the planned timelines:

- Listing: List of locations, names, and phone numbers of households (2000) per admin level with actual mobile network – sent to the server.

- Data collection: At least 1400+ finalized questionnaires sent to the server, in addition to any number of incomplete surveys to capture non-response.

- Recordings: Transcripts and raw recordings cleaned and translated into English or French for remote surveys at the household level.

- Final report: report at the end of the study and data processing, if required.

# ADMINSTRATION AND REPORTING

The CO, Regional Office and HQ team will be required to maintain contact through weekly progress reports, particularly during the hiring, acquisition of visas/travel arrangements and translation/contextualization of questionnaires.

During the data collection phase, these reports may be required on daily or bi-weekly basis as data is uploaded and reviewed for data quality checks. These updates shall contain information such as number of interviews successfully completed, any technical or operational challenges encountered, and any other information relevant to the successful implementation of the survey.

For the purposes of this study, supervision, communications (enquiries and reports) and management will be directly under RAM-HQ in Rome. The focal person for all communications will be Alirah Weyori (alirah.weyori@wfp.org) copying Mohamed Salem (Mohamed.salem@wfp.org).

# TENTATIVE TIMELINE AND KEY MILESTONES

| L'heure Activity | April - May |  | July – August 2024 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 |
| - Questionnaire adaptation to BF context | Completed |  |  |  |  |  |  |  |  |
| - Census of households in ADMIN5 |  |  |  |  |  |  |  |  |  |
| - Training of Enumerators |  |  |  |  |  |  |  |  |  |
| - Testing of Questionnaire |  |  |  |  |  |  |  |  |  |
| - Data Collection |  |  |  |  |  |  |  |  |  |
| - Final Dataset & Report |  |  |  |  |  |  |  |  |  |

Note W=Week

# RELEVANT DOCUMENTATION

- Consolidated Approach for Reporting Indicators of Food Security (CARI) Guidelines - Third edition

- Consolidated Approach for Reporting Indicators of Food Security (CARI) Guidelines - Second edition

- CARI & IPC Factsheet: Technical Annex

# GLOSSARY AND DEFINITION OF TERMS

- Food consumption score (FCS) - The Food Consumption Score (FCS) is the most used food security indicator by WFP and partners. This indicator is a composite score based on households’ dietary diversity, food frequency, and relative nutritional importance of different food groups. The FCS is calculated by inspecting how often households consume food items from the different food groups during a 7-day reference period.  In addition to this, the FCS module collects data on sources of the consumed foods acquired by households.

- Reduced Coping Strategy Index (rCSI) - is an indicator used to compare the hardship faced by households due to shortage of food. The index measures the frequency and severity of the food consumption behaviors the households had to engage in due to food shortage in the 7 days prior to the survey.

- Livelihood Coping Strategies - Essential Needs (LCS-EN) is an indicator used to understand the medium and longer-term coping capacity of households and their ability to overcome challenges in meeting their essential needs in the future.

- Economic Capacity to Meet Essential Needs (ECMEN) - The ECMEN indicator identifies the percentage of households whose expenditures exceeds the Minimum Expenditure Basket (MEB).

- Minimum Expenditure Basket (MEB) - The MEB is defined as what a household requires to meet their essential needs, on a regular or seasonal basis, and its cost. The MEB covers those needs that households meet fully or partially through the market.

- Food Expenditure Share (FES) - Is an indicator used to measure households’ economic vulnerability. It determines the economic vulnerability without the need to have reference to a poverty line or minimum expenditure basket.

  - Expenditure on food items (30-day recall)

  - Expenditures on non-food items (30-day recall)

  - Non-food items (six-month recall

- Household Hunger Score (HHS) - The Household Hunger Scale (HHS) is a simple indicator used to measure household hunger within food-insecure areas. It has been developed and validated for cross-cultural use.

- Individual Dietary Diversity (MDDI) - is a proxy indicator that assesses an individual’s micronutrient adequacy and diet quality. It measures the average number of different pre-determined food groups consumed by the individual the previous day and night (i.e., if the individual met the threshold of five or more groups out of the ten defined food groups).

- Wealth index (WI) - The wealth index (WI) is a composite index composed of key asset ownership variables; it is used as a proxy indicator for household wealth and thus the households’ ability to cope with shocks that leave it vulnerability to poverty and or food insecurity.

# Roles and responsibilities of the Team rCARI - Burkina Faso

| Phase | Activity | Responsibility |
| --- | --- | --- |
| Preparation | Discuss and agree on a budget and timeline for the rCARI study | CO-VAM (Faroukou GARBA, KABRE Moumouni), HQ - RAM (Alirah, Cassandra, Jonas), RB – Fatou |
| Preparation | Share survey instruments and training materials with the Country Office for contextualization. | RB – Fatou & HQ - RAM (Cassandra) |
| Preparation | Review the materials shared to contextualise them and provide feedback, as necessary | CO-VAM (Faroukou GARBA, KABRE Moumouni), |
| Preparation | Contract service providers to conduct the household level data collection. | CO-VAM -> Service provider (AMR & ADKONTACT) |
| Preparation | Recruit relevant on- and off-field enumerators & supervisors to conduct the F2F and Phone interviews. | Service providers (ICASEES) |
| Preparation | Obtain necessary documentation and arrange for visa to enter the country to conduct the training | CO team, HQ - RAM (Cassandra, Jonas) |
| Preparation | Conduct the listing of households to be interviewed for the study in Burkina Faso. At the same time, making the initial contact with households to inform about possible selection for the study (both F2F and phone-based). | CO-VAM -> Service provider (AMR) |
| Preparation | Random assignment of the households into two groups (A and B) | HQ - RAM-N (Alirah) |
| Preparation | Ensure that there is a venue for the training of enumerators. Ensure that there is the catering (drinks (water) and coffee breaks), Ensure the materials for the training (including tablets, a projector, flipchart, markers, notebooks and pens). Provide transportation for the enumerator field visit during questionnaire testing. Prepare a list of phone numbers for the remote testing | CO-VAM - Faroukou GARBA, KABRE Moumouni |
| Training | Lead/support the implementation of the training, answering questions about the indicators and the methodology. | RB – Fatou & RAM (Alirah, Cassandra, Jonas), CO-VAM - Faroukou GARBA, KABRE Moumouni |
| Training | Test the final Questionnaire & provide feedback for adjustments of the questionnaire after testing. | CO-VAM -> Service provider (AMR & ADKONTACT) |
| Training | Lead the field exercise (both F2F and remote) in collaboration with WFP RAM teams. Identify specific questions after field testing of questionnaire to be adjusted providing the correct wording or phrase(s) to reflect country specific nuances. | CO-VAM (Faroukou GARBA, KABRE Moumouni), RB, HQ |
| Training | Adjust the questionnaire in XLSForm after testing if necessary. | HQ – RAM-N (Alirah, Cassandra) |
| Data collection | Provide logistics required for the field survey. Ensure that the data is uploaded to the server daily for verification by WFP RAM teams, ensuring data privacy for all respondents during data collection, storage, and data transfers to WFP. | Service provider (AMR) |
| Data collection | Carry out verifications of data quality on the server and data downloaded by MoDA, | HQ – RAM-N (Nicole) |
| Data collection | Carry out data quality assurance and ensure that checks are put in place for incoming data from the field with poor data quality compensated in required samples. Communicate regularly with RAM-N HQ (Nicole) to feedback any data quality issues during the data collection in the field. | HQ – RAM-N (Alirah, Cassandra & Jonas) & RB and CO (Salifousanda) |
| Data cleaning | Transcripts and raw recordings cleaned and translated into English or French for remote surveys at the household level. | CO-VAM -> Service provider (ADKONTACT) |
| Data cleaning | Clean, and submit the final dataset in English using standard WFP variable names in SPSS or Stata formats. | HQ RAM-N (Alirah & Nicole) |
| Data analysis and reporting | Final report at the end of the survey and data processing, detailing the sampling, weights, composition of respondents, their distribution and any syntax used the initial statistics | HQ – RAM-N (Alirah) |