rCARI Validation Study: APP-AF Implementation Team’s Terms of Reference (TOR) for

Mauritania CO Mission

Background & purpose

During the COVID-19 pandemic, there was an urgent need to develop a methodology to assess food security in a timely manner, without exposing enumerators to the risk of infection. The WFP thus developed and used quick and easy-to-administer questionnaires to assess the food security situation of the population over the phone. A remote version of the Consolidated Approach for Reporting Food Insecurity (rCARI) was developed as an adaptation of the standard CARI methodology to report on food insecurity. Although the rCARI methodology is gradually gaining acceptance in most WFP country offices because of its ease of use, empirically, it has not yet been validated against the standard CARI.

The study is being piloted across six countries in Africa, Latin America, the Middle East, and Asia. Burkina Faso CO is among 6 countries globally selected to pilot a study to validate the rCARI methodology against the standard CARI methodology of reporting food insecurity.

With the overall objective of providing evidence to support the use of remote data collection to report food insecurity in real time particularly for inaccessible areas, the purpose of the mission is:

- To implement a survey experiment to collect data through Face-to-Face (F2F) and Remote modalities in 40-45 selected villages in Centre-Nord, Nord, and Plateau Central Prefectures in Burkina Faso.

Scope, procedures, and timelines

The mission will take place 26 June to 30 August 2024 and will be led by the Weyori Alirah, HQ AAP-FA officer. Individual areas shall be planned and prioritised in liaison with the country office RAM team which will be led by Mebenga Jeanclaude.

Activities under each phase of Review

| Phases of Review | Activities | Responsibility | Timeline |
| --- | --- | --- | --- |
| PHASE 1 Village Census Exercise | - Brief to the CO management on the mission objectives, activities and intended outcomes | CO RAM/HQ | 1 July |
|  | - Conduct census of 37 villages selected by CO | CO RAM/HQ | 1 – 6 July |
| PHASE 2 In person Training of Enumerators | - Arrival of training facilitators | RB/HQ | 7 July |
|  | - Start of enumerator training (Face-to-Face and Remote) | RB/RAM | 8 – 12 July |
|  | - Field testing of instruments | CO RAM/RB/HQ | 12 July |
| PHASE 3 Data Collection (F2F and Remote) | - Face-to-Face interviews of sampled households | CO RAM/HQ | Week of 15 July |
|  | - Remote interviews of sampled households | CO RAM/HQ | Week of 15 July |
|  | - High frequency monitoring | CO RAM/HQ | Week of 15 July |
|  | - Debrief to CO management and CO RAM on the progress of the exercise | HQ | Week of 5 August |